## POAM
POA&M ID | Control ID | Weakness | Risk Level | Responsible Party | Completion Date | Status
POA-001 | UBTU-24-600090 | Root filesystem partitions are not encrypted at rest (LUKS not configured). Finding is environment-inherent: lab VM runs under WSL2, which does not support block-level disk encryption. | High | System Owner | 2026-12-05 | Open
POA-002 | UBTU-24-700320 | APT is not configured to automatically remove obsolete package versions after updates, allowing stale packages to persist on disk. | Low | System Owner | 2026-10-06 | Open
POA-003 | UBTU-24-200680 | SSH client is not configured to display a login confirmation banner prior to establishing a remote connection. | Medium | System Owner | 2026-11-05 | Open
POA-004 | UBTU-24-100510 | AppArmor is installed but not actively enforcing profiles across all required system services. | Medium | System Owner | 2026-11-05 | Open
POA-005 | UBTU-24-100850 | SSH client is not restricted to FIPS 140-3 validated ciphers; non-approved cipher suites remain enabled. | Medium | System Owner | 2026-11-05 | Open
POA-006 | UBTU-24-400360 | SSSD is not configured with a defined certificate trust anchor path for validating client certificates. | Medium | System Owner | 2026-11-20 | Open
POA-007 | UBTU-24-400370 | SSSD does not have certificate-based user mapping enabled, limiting smart card / PKI authentication support. | Medium | System Owner | 2026-11-20 | Open

## Notes
POAM Structure Notes
Source: Post-hardening OpenSCAP scan (STIG profile: xccdf_org.ssgproject.content_profile_stig,
Canonical Ubuntu 24.04 LTS STIG V1R5), scanned after Ansible remediation applied 13 changes.
Risk Level mapping (per STIG severity category):
CAT I = High
CAT II = Medium
CAT III = Low
Completion dates set 30-90 days from scan date (2026-09-06), scaled to risk level.
POA-001 (Encrypt Partitions) is accepted risk in this lab environment: WSL2 does not
support LUKS block-level disk encryption. On a physical or cloud VM deployment, this
control would be remediated directly rather than tracked as a POAM item.